Employee Skill Catalog and Skill Profile Management

BC Tech Days 26 (Demo)

Fernando Artigas Alfonso

2026-06-10

| Date | PreparedBy | version | DsdTicket |
| --- | --- | --- | --- |
| 2026-06-10 | Fernando Artigas Alfonso | 1.0 | CCN-001 |

1. {{Label_Section_Header}}	1

2. {{Label_Section_BusinessContext}}	2

3. {{Label_Section_ProposedSolution}}	3

4. {{Label_Section_Architecture}}	4

5. {{Label_Section_FeasibilityAnalysis}}	5

6. {{Label_Section_TimeEstimate}}	6

7. {{Label_Section_TestingSetup}}	7

8. {{Label_Section_TestingSteps}}	8

9. {{Label_Section_Recommendation}}	9

10. {{Label_Section_Approvals}}	10

# 1. Header

| Field | Value |
| --- | --- |
| CCN ID | CCN-001 |
| Title | Employee Skill Catalog and Skill Profile Management |
| Customer | BC Tech Days 26 (Demo) |
| DSD Ticket | TBD |
| BC Environment | BC Tech Days 2026 sandbox |
| BC Version Baseline | application 22.0.0.0 / runtime 15.2 |
| Extension Affected | Employee Skill Management (ESM) |
| Source User Story | US-001 |
| Source Spec | SPEC-001 |
| Architecture | ARCH-001 |
| Analysis | ANALYSIS-001 |
| Prepared By | Fernando Artigas Alfonso |
| Date | 2026-06-10 |
| Status | Pending Approval |
| Recommendation | GO |

# 2. Business context

Who: HR administrators, line managers, and employees of BC Tech Days 2026.

What: Introduce a central, auditable skill catalog and an effective-dated employee skill assessment ledger inside Business Central.

Why: Skills are currently tracked informally in spreadsheets outside BC — with no shared catalog, no agreed proficiency scale, and no history preservation. When a skill assessment changes, the previous value is overwritten and lost. This blocks consistent competency reporting and auditability.

Objective: Deliver a greenfield Business Central extension (Employee Skill Management — ESM) that replaces spreadsheet-based skill tracking with an auditable, effective-dated ledger embedded in the standard Employee Card.

Functional scope summary:

| AC | Title | Key behaviour |
| --- | --- | --- |
| AC1 | Skill catalog maintenance | Create/edit/block skills with unique code; deletion blocked when in use |
| AC2 | Employee skill profile maintenance | Add catalog-only skills per employee; current = latest confirmed effective assessment |
| AC3 | Effective-dated skill assessment | Mandatory effective date; "current" = latest Confirmed row on or before work date |
| AC4 | Immutable skill history and auditability | No overwrite/delete of prior entries; read-only history for non-admins |

Out of scope (this CCN): Development goals (US-002), performance reviews (US-003), training plans (US-004), reward eligibility (US-005), LMS integration, configurable proficiency scale, assessment correction mechanism, API pages, telemetry.

# 3. Proposed solution

The change introduces a greenfield AL extension with 14 objects across 2 delivery phases. No existing BC standard objects are modified — all touches to Employee Card (Page 5200) are via PageExtension.

AL Object Inventory

| Category | Count | Object IDs |
| --- | --- | --- |
| Enums | 2 | 51100–51101 |
| Tables (new) | 3 | 51100–51102 |
| Pages (new) | 5 | 51100–51104 |
| Codeunit (new) | 1 | 51100 (5 procedures) |
| Page Extensions (new) | 1 | 51100 |
| Permission Sets (new) | 2 | 51100–51101 |
| Total | 14 | ID range consumed: 51100–51104 |

Key design decisions

| Decision | Choice |
| --- | --- |
| Proficiency scale | Fixed enum: Beginner / Intermediate / Advanced / Expert (Enum 51100) |
| Who may enter assessments | HR/manager (→ Confirmed) and employee self-service (→ Pending Confirmation) |
| Confirmation workflow | ESM FULL users confirm Pending rows via Confirm action on Employee Skill Profile ListPart |
| Assessment mutability | Append-only ledger — OnBeforeModify and OnBeforeDelete raise unconditional errors |
| Profile page UX | Inline editable ListPart (no dialog page); Pending rows rendered in Ambiguous (orange) style |
| Current proficiency | On-demand via GetCurrentProficiency; filters to Confirmed rows only |

Delivery phases

| Phase | Scope | Effort |
| --- | --- | --- |
| Phase 1 — Catalog Foundation | Enums 51100/51101; Tables 51100/51101; Pages 51100/51101/51102; Permission Sets 51100/51101 | 5–7 h |
| Phase 2 — Employee Assessments | Table 51102; Codeunit 51100; Pages 51103/51104; PageExtension 51100; permission set updates | 9–13 h |

Open Questions resolution

| OQ | Status | Resolution |
| --- | --- | --- |
| OQ1 — Proficiency scale | Resolved | Fixed 4-level enum |
| OQ2 — Self-service & confirmation | Resolved | Employee entries start as Pending; ESM FULL users confirm |
| OQ3 — Correction mechanism | Resolved (deferred) | No correction in v1; counter-entry pattern planned for future story |
| OQ4 — Profile page UX | Resolved | Inline editable ListPart |

# 4. Architecture solution

Architecture document: ARCH-001 — see openspec/architecture/ARCH-001-employee-skill-catalog-and-profile.architecture.md

Architectural style: Master-data / append-only ledger (analogous to G/L Entry, Item Ledger Entry). Business logic concentrated in Codeunit 51100 "Skill Mgt." (codeunit-as-service pattern). Pages are thin and delegate all writes to the codeunit.

ADR summary:

| ADR | Decision |
| --- | --- |
| ADR-1 | Table 51102 append-only: unconditional errors in OnBeforeModify and OnBeforeDelete |
| ADR-2 | Current proficiency computed on demand via GetCurrentProficiency; no FlowField or denormalised store |
| ADR-3 | ConfirmAssessment uses ModifyAll on PK to bypass OnBeforeModify; procedure is internal to Codeunit 51100 |
| ADR-4 | Inline editable ListPart with OnBeforeInsert permission-driven InitialStatus; Pending rows styled Ambiguous |
| ADR-5 | Two standard permission sets (ESM BASIC / ESM FULL) — no custom user setup table |

Standard BC objects touched:

| Object | Touched by | Nature |
| --- | --- | --- |
| Employee Card (Page 5200) | PageExtension 51100 | One FactBox + one navigation action added; no fields or triggers modified |
| Employee (Table 5200) | Table 51102 FK | TableRelation: Employee.No. on Field 2; no triggers or fields on Table 5200 modified |

Key constraints: C-5 — runtime permission guard absent from ConfirmAssessment (mandatory review item); C-7 — concurrent confirmation race condition (acceptable for v1).

# 5. Feasibility analysis

Analysis document: ANALYSIS-001 — see openspec/analysis/ANALYSIS-001-employee-skill-catalog-and-profile.analysis.md

Overall risk rating: LOW–MEDIUM

SWOT

Strengths

• Greenfield extension — zero conflict with existing objects; full ID range available

• All 4 Open Questions resolved before implementation; no unresolved functional unknowns

• Master-data / ledger pattern is standard in BC; familiar to any BC developer

• Phase 1 independently deployable; unblocks US-002 through US-005 immediately

Weaknesses

• ConfirmAssessment uses a non-standard ModifyAll bypass (ARCH-001 ADR-3) — requires explicit developer awareness

• No correction mechanism in v1 — incorrectly confirmed entries are permanent

• Runtime permission guard absent from ConfirmAssessment at codeunit level (flagged as mandatory review item)

• No automated test codeunits in scope

Opportunities

• Foundation for 4 downstream stories (US-002 to US-005)

• RapidStart-ready catalog tables for fast customer onboarding

• Natural telemetry target for Application Insights in a follow-on story

Threats

• Cost of not implementing: skills remain in spreadsheets; US-002 to US-005 blocked entirely

• Scope creep post-go-live from HR stakeholders; controlled by CCN process

• BC runtime version mismatch could invalidate ADR-3 assumptions (R-01, mitigated by sandbox verification)

Risk register

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | ConfirmAssessment ModifyAll bypass behaves unexpectedly on target BC runtime | Low | High | Verify on target sandbox before Phase 2 merge |
| R-02 | HR users demand correction mechanism post-go-live | Medium | Medium | Brief HR users pre-go-live; correction-entry pattern logged as future story |
| R-03 | Missing runtime permission guard in ConfirmAssessment allows privilege escalation | Low | Medium | Blocking AL Reviewer comment; add UserHasESMFullPermission() guard in procedure |
| R-04 | GetCurrentProficiency performance at scale (>200 entries per employee+skill) | Low | Low | SetLoadFields + secondary key; bulk-import out of scope for v1 |
| R-05 | Phase 1 delay blocks US-002 spec work | Low | Medium | Phase 1 is 5–7 h; merge independently before US-002 development |
| R-06 | Concurrent confirmation audit stamp discrepancy | Low | Low | Acceptable for v1; LockTable guard deferred |

# 6. Time estimate

Rate: 100 EUR/h · 1 developer · 8 h/day. 20% contingency applied to Expected total.

Hours by phase

| Phase | Optimistic | Expected | Pessimistic |
| --- | --- | --- | --- |
| Phase 1 — Catalog Foundation | 4.5 h | 6 h | 7 h |
| Phase 2 — Employee Assessments | 8.5 h | 11 h | 13 h |
| Code review (1 round) | 1 h | 1.5 h | 2 h |
| Integration testing on sandbox | 1 h | 1.5 h | 2 h |
| Subtotal | 15 h | 20 h | 24 h |
| Contingency (20% on Expected) | — | 4 h | — |
| Total | 15 h | 24 h | 24 h |

Calendar duration

| Scenario | Hours | Working days |
| --- | --- | --- |
| Optimistic | 15 h | 2 days |
| Expected (with contingency) | 24 h | 3 days |
| Pessimistic | 24 h | 3 days |

Cost estimate

| Scenario | Hours | Total (EUR) |
| --- | --- | --- |
| Optimistic | 15 h | 1,500 EUR |
| Expected | 24 h | 2,400 EUR |
| Pessimistic | 24 h | 2,400 EUR |

Excludes VAT, project management, deployment coordination, and user training. Assisted go-live: +1–2 h (100–200 EUR) not included above.

# 7. Testing setup (planned)

| Phase | Test scope | Exit gate |
| --- | --- | --- |
| Phase 1 | Skill/Category CRUD; delete guards (blocked skill, skill with assessments, category with skills); permission set read-only verification | All Phase 1 AC1 tests green on sandbox |
| Phase 2 | AddSkillAssessment inserts (Confirmed + Pending paths); GetCurrentProficiency effective-date logic; immutability errors on modify/delete; ConfirmAssessment status transition; Employee Card FactBox and Skill History page; ESM BASIC / FULL role verification | All Phase 2 AC2–AC4 tests green; ESM FULL permission guard present in codeunit |

# 8. Testing steps (acceptance, executed by Customer)

The following acceptance steps are to be executed by the Customer on a BC sandbox with representative employee and skill catalog data.

1. AC1 — Skill catalog: Create a Skill Category and 3 Skills referencing it. Edit a Skill description. Block a Skill. Attempt to delete the blocked Skill — verify it can be deleted (Blocked ≠ In Use). Attempt to delete a Skill with an employee assessment — verify deletion is blocked with an error message.

2. AC2 — Employee profile (HR path): Open an Employee Card as an ESM FULL user. In the Skill Profile FactBox, enter a new row (Skill Code, Proficiency Level, Effective Date). Verify the row appears without orange styling (Status = Confirmed).

3. AC2 — Employee profile (self-service path): Open an Employee Card as an ESM BASIC user. Enter a new row. Verify the row appears in orange (Status = Pending Confirmation). Verify the Confirm action is not visible.

4. AC2 — Confirmation: Log in as an ESM FULL user. Select the orange Pending row. Invoke the Confirm action. Verify the row is no longer orange and Status shows Confirmed.

5. AC3 — Effective date: Add two assessments for the same employee + skill with different effective dates (one past, one future). Call the Skill History page and verify both rows are present. Verify the current proficiency in the FactBox matches the most recent Confirmed row on or before today.

6. AC4 — Immutability: Attempt to edit any field of an existing assessment row in the Skill History page — verify the page is read-only. Verify no Delete action is available on the history page.

# 9. Recommendation

GO — unconditional

SPEC-001 is technically sound, all 4 Open Questions are resolved, and the design is 100% additive (no existing BC objects modified). At an expected 24 h / 2,400 EUR it is a well-scoped, low-risk delivery that directly unblocks four subsequent user stories.

Non-blocking advisories before developer handoff:

1. Add a runtime UserHasESMFullPermission() guard as the first statement of ConfirmAssessment (ARCH-001 C-5) — mandatory AL Reviewer check.

2. Confirm target sandbox matches application 22.0.0.0 / runtime 15.2 declared in app.json.

3. Define at least one test codeunit per phase as a merge pre-condition.

4. Reserve initial skill catalog data population as a separate go-live activity (not in the estimate).

# 10. Approvals

| Role | Name | Decision | Date |
| --- | --- | --- | --- |
| Project Sponsor |  | Pending |  |
| Technical Lead |  | Pending |  |
| AL Analyst | Fernando Artigas Alfonso | GO | 2026-06-10 |

| Field | Value |
| --- | --- |
| CCN Nr. | CCN-001 |
| Spec Reference | SPEC-001 |
| Architecture Reference | ARCH-001 |
| User Story | US-001 |
| Module | Human Resources |
| Priority | High |
| Date | 2026-06-10 |
| Prepared By | AL Analyst |
| Rate Assumption | 100 EUR/h · 1 developer · 8 h/day |
| Status | Pending Approval |